## Scorecard
Lodestar Eval Scorecard
2026-07-02 · L3 vs PROVISIONAL gold (human sign-off pending) · tally: 17 PASS / 12 FAIL / 2 PENDING-BLOCKED / 3 OPEN
Layer | Metric | Dimension | Target | Actual | Verdict | Notes
L1 Prompts | Schema/consumer drift, 13 prompts (GATE) | Correctness | 0 | 0 | PASS | prompt_audit.py rerunnable in CI
L1 Prompts | Rubric score per prompt | Correctness | 13/13 Green (>=80%) | 11/13 — Strategist 70.8%, Ask 75.0% | FAIL | No worked examples; no version markers
L2 Extraction | Strictly grounded (live judged, n=94) | Faithfulness | >=90% | 84.0% | FAIL | Single in-session judge, flagged
L2 Extraction | Fabricated entities/numbers | Faithfulness | 0 | 3 (BlackRock; 916 vs 674 turbines; 63 kWh) | FAIL | Each re-verified vs raw source
L2 Extraction | Provenance coverage | Faithfulness | >=95% | 95.6% | PASS | tags field still untracked
L2 Extraction | Cross-feed duplicate URLs | Correctness | 0 | 1 in sample + 53 slash-dups full-table | FAIL | No URL normalization at write
L3 MOT Lens | Gold set human-verified | — | >=150 | 199 provisional, 0 human-signed | PENDING | 36 disputed rows triaged, ~1 hr review
L3 MOT Lens | maturity_stage exact (n=146) | Correctness | >=70% | 69.2% (Wilson 95% CI 61.3–76.1%) | FAIL | Marginal; inside CI of target
L3 MOT Lens | maturity_stage within-1 | Correctness | >=90% | 82.9% | FAIL | 44% of errors are n/a-boundary
L3 MOT Lens | adoption_stage exact (n=146) | Correctness | >=65% | 71.9% (CI 64.1–78.6%) | PASS
L3 MOT Lens | adoption_stage within-1 | Correctness | >=90% | 86.3% | FAIL | Chasm boundary dominates
L3 MOT Lens | business_impact exact | Correctness | >=80% | 94.5% (CI 89.6–97.2%) | PASS
L3 MOT Lens | scope exact | Correctness | >=80% | 95.9% (CI 91.3–98.1%) | PASS
L3 MOT Lens | Stage errors adjacent | Calibration | >=80% | 80% maturity / 95% adoption (stage-to-stage) | PASS* | * n/a confusions are the real failure mode
L3 MOT Lens | A/B: deployed prompt vs stored labels | Correctness | v2 >= v1 | v2 −5.5pp maturity, −6.8pp adoption | FAIL | Fable 5 baseline to beat: 63.0%/63.7%
L4 Rollup | Recompute vs stored drift | Correctness | 0 | 0 (232 feed-days, 10 feeds) | PASS | Live-verified
L4 Rollup | Open bugs | Correctness | — | 3 (query-string dedup; momentum; breakdown unchecked) | OPEN | All repro'd offline
L5 Tech layer | Placement/transition fixtures | Correctness | 100% | 100% (16 golden tests added, 1 xfail) | PASS | xfail pins modal-vs-committed gap
L5 Tech layer | Cross-surface stage disagreement | Completeness | 0 | 0 | PASS | Single display_stage() source verified
L6 Financials | Fundamentals within ±5% (5 tickers, live) | Correctness | 5/5 | 3/5 — Samsung +12.8%, ASML −5.7% | FAIL | Stale 2-yr-old static FX map
L6 Financials | Event-study baseline strictly-before | Correctness | 100% | Verified (NVDA 2026-05-20 → 05-19) | PASS
L6 Financials | Fiscal-period alignment | Correctness | correct | _first() can mix years; 0/5 fired today | OPEN | 2x rd_intensity repro
L7 Forecasts | Look-ahead violations | Calibration | 0 | 0 (35/36 re-derived; 36th snapshot-audited) | PASS
L7 Forecasts | Brier + calibration recompute | Calibration | exact | Exact (0.889 acc / 0.119 Brier) | PASS | Record is under-confident
L7 Forecasts | Locked-when-made | Calibration | holds | 118/118 fingerprints recompute | PASS | No DB-level immutability (convention)
L7 Forecasts | Price-call quarantine | Calibration | 100% | Headline pools them — latent −20.5pp cliff ~Sep 2026 | FAIL | 0.889→0.684 with no skill change
L8 Strategist | Numeric-claim grounding | Faithfulness | >=95%, 0 hallucinated | 100% adjudicated, 0 fabrications | PASS | 4 flags were unit conversions (harness fix)
L8 Strategist | S#/T# reference validity | Faithfulness | 100% | 100% | PASS
L8 Strategist | Theory fidelity (mean /3) | Theory | >=2.0, 0 misapplications | 1.6, 2 misapplications | FAIL | Dominant-design off 1–2 pts; post-hoc chasm
L8 Strategist | Falsifier quality (mean /12) | Calibration | >=9, none missing | 10.8, none missing/non-refuting | PASS
L8 Strategist | Overclaim rate | Theory | <=10% | 20% deterministic / 40% panel | FAIL | In-session panel, flagged
L9 Ask | Retrieval precision@5 (context precision) | Correctness | >=0.80 | 0.94 | PASS | 29 live retrievals; in-session judged
L9 Ask | Phantom-citation guard | Faithfulness | exists | Absent in production | FAIL | Static finding; live unmeasured
L9 Ask | Faithfulness / refusal (answer leg) | Faithfulness | 0 ungrounded / >=90% | Unmeasured — TOQAN_ASK empty in .env | BLOCKED | Harness ready; captures saved
L10 App | Filters/toggles change the view | Completeness | 100% | 21/21 wired; 0 console errors; 7/7 tabs live | PASS | Scope fix only in working tree — commit it
L10 App | Unrendered API fields | Completeness | 0 | 8 top-level + nested drops | FAIL | Incl. duplicated adoption insight
L10 App | Cross-tab contradictions | Completeness | 0 | 1 (Coverage) + backward transitions hidden | FAIL

## Confusion
Lens error pairs — gold vs predicted
Live run vs provisional gold, n=146 joined (correct: maturity 101, adoption 105, impact 138, scope 140)
Field | Gold label | Predicted | Count | Error type
maturity_stage | dominant-design | n/a | 4 | n/a boundary
maturity_stage | dominant-design | growth | 2 | adjacent
maturity_stage | dominant-design | emerging | 1 | non-adjacent
maturity_stage | emerging | research | 7 | adjacent
maturity_stage | emerging | growth | 3 | adjacent
maturity_stage | emerging | n/a | 2 | n/a boundary
maturity_stage | growth | emerging | 7 | adjacent
maturity_stage | growth | n/a | 4 | n/a boundary
maturity_stage | growth | dominant-design | 1 | adjacent
maturity_stage | mature | emerging | 3 | non-adjacent
maturity_stage | mature | n/a | 3 | n/a boundary
maturity_stage | mature | growth | 1 | non-adjacent
maturity_stage | n/a | emerging | 2 | n/a boundary
maturity_stage | n/a | dominant-design | 1 | n/a boundary
maturity_stage | n/a | mature | 1 | n/a boundary
maturity_stage | research | n/a | 3 | n/a boundary
adoption_stage | early-majority | early-adopters | 13 | adjacent
adoption_stage | early-majority | n/a | 6 | n/a boundary
adoption_stage | early-majority | innovators | 1 | non-adjacent
adoption_stage | early-majority | late-majority | 1 | adjacent
adoption_stage | early-adopters | innovators | 4 | adjacent
adoption_stage | early-adopters | n/a | 2 | n/a boundary
adoption_stage | early-adopters | early-majority | 1 | adjacent
adoption_stage | innovators | early-adopters | 2 | adjacent
adoption_stage | innovators | n/a | 1 | n/a boundary
adoption_stage | n/a | early-majority | 6 | n/a boundary
adoption_stage | n/a | innovators | 4 | n/a boundary
business_impact | material | contextual | 5 | —
business_impact | contextual | material | 2 | —
business_impact | contextual | none | 1 | —
scope | deal | single-company | 2 | —
scope | deal | regulatory | 1 | —
scope | single-company | comparison | 1 | —
scope | single-company | deal | 1 | —
scope | single-company | regulatory | 1 | —

## Fix backlog
Prioritized fix backlog
P0 = trust blockers (fix before showing anyone) · P1 = quality · P2 = product (council). Effort: XS<0.5d, S=0.5–1d, M=2–5d, L>5d
Priority | # | Fix | Layer | Effort | Evidence / why
P0 | 1 | Dated live FX (replace static map; store rate + as-of date) | L6 | S | Samsung +12.8% live-confirmed on flagship 2x2
P0 | 2 | Exclude quarantined price calls from headline accuracy/Brier | L7 | S | Headline drops 0.889→0.684 ~Sep 2026 with no skill change
P0 | 3 | Ask citation guard (range-check [S#]/[T#]); drop doctrine fallback; populate TOQAN_ASK | L9 | S | Phantom citations possible by construction; key empty
P0 | 4 | Lens n/a gate in MOT Lens prompt (corp-finance→n/a; funding≠chasm; boundary debias) → re-A/B | L3 | M | 44% of maturity errors are n/a-boundary; lens_ab.py ready
P0 | 5 | Pre-write groundedness check: summary entities+numbers must appear in source | L2 | M | 3/94 live fabrications passed all validation
P0 | 6 | Commit working-tree backend/app/mot.py scope-filter fix | L10 | XS | At HEAD the domain filter is a silent no-op
P0 | 7 | Fiscal-period alignment in finance/client.py _first() | L6 | S | R&D-intensity 2x error repro'd; latent on live data
P0 | 8 | URL normalization + cross-feed dedup at write time | L2/L4 | M | 1 cross-feed + 53 slash-dups live; query-string overmerge
P1 | 9 | Strategist prompt rewrite: worked examples, sparse-pack rule, overclaim ban, precondition evidencing | L1/L8 | M | Fidelity 1.6/3, overclaim 20–40%, prompt scored 70.8% Amber
P1 | 10 | Ask prompt: refusal example + phantom-citation ban; version headers on 12 prompts | L1 | S | Ask 75% Amber; only lens prompt versioned
P1 | 11 | Momentum off-by-one (trends.py) + add by_company_breakdown to rollup integrity | L4 | S | Flat volume reads +20%; breakdown unchecked
P1 | 12 | Guard POST /api/forecasts/resolve (kind/status check) | L7 | XS | Any pred_id re-gradeable via API
P1 | 13 | Persist committed (not modal) stage to history | L5 | S | Transition labels can name stages no surface showed (xfail pinned)
P1 | 14 | Restore backward transitions in UI; fix duplicated adoption_interpret; render/drop 8 dead fields | L10 | S | Hiding disconfirming evidence; corp-dev blocker
P1 | 15 | Small-base threshold on trend % display | L4/UI | XS | '+13155%' procurement-killer artifact
P1 | 16 | tags provenance; ledger dropped-item identities | L2 | XS | Last untracked field; drops only go to stdout
P2 | 17 | Public timestamped ledger page; per-technology forecast pages; calibration curve as homepage | Product | M | Council: the one artifact incumbents cannot copy
P2 | 18 | Re-run L8 judge with independent Toqan judges; enforce precondition evidencing in schema | Product | M | In-session panel has correlated-judge bias
P2 | 19 | API keys + custom company registry + Slack/webhook transition alerts | Product | M-L | Unlocks corp-dev $30–50k/yr
P2 | 20 | Transition-vs-outcome validation study over technology_stage_history | Product | M | Proves 'leading indicator, not post-hoc'
P2 | 21 | Rolling gold refresh (~25 labels/mo) + point-in-time label snapshots | Product | M | 54/200 gold URLs already aged out; churn unmeasurable without vintages
P2 | 22 | Methodology/as-of footers on Capital; peer-set benchmarking; evidence packs | Product | M | Partner/analyst table stakes

## Product backlog
Council product backlog (advantage ÷ effort)
From 20_product_completeness.md §C · QW = quick win, MB = moat-builder · Would-pay: Partner $30–50k/yr/team · Corp-dev $30–50k/yr (API+registry) · VC $5–10k/seat (with 2-yr record)
Rank | Move | Tag | Effort | Type | Unlocks | Why now
1 | Honest headline (exclude price calls; per-category + difficulty-weighted) | method | S | QW | All six personas | Cliff fires ~Sep 2026 — fix before exposed
2 | Data floor: dated FX + fiscal alignment + surface missing R&D as n/a | data | S | QW | Partner, Analyst | Two live-confirmed bugs on flagship exhibit
3 | Gate the lens (n/a rule, funding≠chasm, boundary debias) + measure vs gold | method | M | QW→MB | VC, Scholar, Corp-dev | Every purchasable exhibit sits on the maturity label
4 | Finish human gold set (>=150) + publish accuracy, within-1, confusion, kappa | method | M | QW | Scholar, VC, Skeptic minimum | Already triaged to 36 disputed rows
5 | Restore backward transitions + transition provenance + event dates in tooltips | UX | S | QW | Corp-dev, Analyst | Hiding disconfirming evidence is disqualifying
6 | Ask citation guard + drop doctrine fallback | method | S | QW | Analyst, Partner | Table stakes vs AlphaSense
7 | Kill small-base momentum artifacts | method | XS | QW | Corp-dev | Procurement-killer screenshot today
8 | Methodology + as-of footers on Capital | UX | S | QW | Partner, Analyst | FactSet ships this on every screen
9 | Public ledger page: timestamped, per-tech forecast pages, calibration homepage | positioning | M | MB | All; Skeptic's one bet | The artifact incumbents structurally cannot copy
10 | Run L8 fidelity judge (independent) + enforce precondition evidencing in schema | method | M | MB | Scholar, Partner | Fidelity 1.6/3 measured; instrument now exists
11 | Productize API + custom registry + Slack/webhook alerts | architecture | M-L | MB | Corp-dev $30–50k/yr | Endpoints exist; alerting turns page into pipeline
12 | Transition-vs-outcome validation study | method | M | MB | Scholar, VC | Only way to prove leading-indicator claim; data collected
13 | Rolling gold refresh + point-in-time label snapshots | data | M | MB | Analyst, eval hygiene | Reproducibility; contamination defense
14 | Non-news leading signals (patents/hiring) OR one-vertical depth | data | L | MB | Corp-dev, Skeptic niche | Strategy fork — defer until floor fixed